## Sheet1
Estimation
| Task | Time (hour) | Testing | Fix
1 | Build a structure of project (use Gulp, AngularJS, TypeScript) | 6 |  |  | Total (hours) | 54
2 | Login page |  |  |  | Start date | 2017-01-23
| 2.1 UI | 3 | Passed |  | End date | 2017-02-08
| 2.2 Reponsive | 4 | Passed
| 2.3 Login/Logout | 6 | Passed
| 2.4 Remember Me | 4 | Failed | Passed | Technical skills
3 | User page |  |  |  | AngularJS 1
| 3.1 UI | 4 | Failed | Passed | TypeScript
| 3.2 Reponsive | 3 | Passed |  | SASS (custom + Bootstrap 3)
| 3.3 Search/Paging/Sorting | 4 | Passed |  | Gulp
| 3.4 Add user |  |  |  | PouchDB
| 3.3.1 Form add user | 3 | Passed
| 3.3.2 Validate form | 2 | Passed
| 3.5 Remove user | 1 | Passed
| 3.6 Edit user | 2 | Passed
4 | Group page
| 4.1 UI | 2 | Passed
| 4.2 Reponsive | 1 | Passed
4.3 Add group
| 4.3.1 Form add group | 1 | Passed
| 4.3.2 Validate | 1 | Passed
| 4.4 Remove group | 0.5 | Passed
| 4.5 Edit group | 0.5 | Passed
5 | Configuration page (database, expire login time) | 3 | Failed | Passed
6 | Permission (Admin/Editor/View) | 3 | Passed